## Sheet1
2025 Borough Project: Water, Park, and Streets Timeline
Year |  | Tasks | Date Start | Date End | Description
X | 2025 Constitution Square Basketball and Parking Lot resurface Project: Overlay of courts and parking lot
2025 | Parks Dept Courts | Basketball and Parking lot Overlay Project Borough Council Meeting Approval | 2025-02-04 | 2025-02-04 | Approval for advertise
2025 | Parks Dept Courts | Basketball and Parking lot Overlay Project Award | 2025-02-27 | 2025-02-27 | Council Approval at February 27 Committee Meeting Lowest qualifiying bidder is awarded the project
2025 | Parks Dept Courts | Contractor on site for Basketball and Parking lot Overlay Project | 2025-05-19 | 2025-07-31 | Proposed timeline for Paving Contractor on site
2025 | Parks Dept Courts | The Breneman Company( Costars vendor) | 2025-06-27 | 2025-08-31 | Proposed basketball court coating contractor on site
X | 2025 Street Resurfacing Project: Ultrathin resurface of Lemon Street/ Fog Seal Stevens Street and Hollow Drive
2025 | Street Dept | Lemon St MS944 Ultrathin/ Fog Seal Projecs Borough Council Meeting Approval | 2025-02-04 | 2025-02-04 | Lemon St MS944 Ultrathin / Fog Seal Project Approval to advertise
2025 | Street Dept | Lemon St MS944 Ultrathin/ Fog Seal Projects Award | 2025-02-27 | 2//27/2025 | Council Approval at February 27 Committee Meeting Lowest qualifiying bidder is awarded the project
2025 | Street Dept | Contractor on site for Lemon Street Ultrathin/ Fog Seal | 2025-06-01 | 2025-08-31 | Proposed schedule for contractor on site
x | 2025 Park Grant Playground Renovations Project: Playground and Bathroom improvements project
2025 | Park Grant | Park Grant Project Borough Council Meeting Approval | 2025-02-04 | 2025-02-04 | Park Grant Project Approval for advertise and Penn Bid
2025 | Park Grant | Park Grant Project Bid Award | 2025-04-01 | 2025-04-01 | Council Approval at the April 1, 2025 Council Meeting Lowest qualifiying bidder is awarded the project
2025 | Park Grant | Park Grant project contractor on site | 2025-05-01 | 2025-06-30 | Approx time line, project may commence based on Borough and contractors schedule
2025 | Park Grant | Park Grant Upper Pine Sidewalk replacement | 2025-05-01 | 2025-06-30 | Proposed timeline, Sidewalks replacement along upper Pine St for Park Project
2025 | Park Grant | Park Grant Costars Playgrounf Equipement Installation | 2025-06-01 | 2025-07-31 | Proposed timeline, Costars Contractor to install playground equipement
x | 2025 Pine Street Water Main Project: Replacement of Water main from State St to Hershey Ave
2025 | Water Dept Main | Pine st water project Borough Council Approval | 2/4/2025 | 2/4/2025 | Pine St Water Project Approval for advertise and Penn Bid
2025 | Water Dept Main | Pine st Water Award | 04/01/2025 | 04/01/2025 | Council Approval at the April 1, 2025 Council Meeting Lowest qualifiying bidder is awarded the project
2025 | Water Dept Main | Pine St Water line project contractor on site | May 2025 | August 2025 | Proposed timeline, project may commence based on Borough and contractors schedule